## Timeline
Bluebird Car Rental - Journey Tracking Workplan
Generated: 17 June 2026
Task | Phase | Owner | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Notes
Setup Project & GTM Container | Phase 1 | Ade / Dev | GTM container setup | [5 empty] | Buat GTM container, GA4 tag, Data Layer variable dasar
1.1 Entry & Search (virtualPageview + search) | Phase 1 | Dev Frontend | Implement | Review |  |  |  |  | virtualPageview + search event + parameter service, pickup_area, dll
1.2 Daftar Armada (view_item_list + select_item) | Phase 1 | Dev Frontend | Implement | Review |  |  |  |  | Item list armada dengan item_id stabil dari backend
1.3 Detail Sewa (view_item + fill_rental_detail) | Phase 1 | Dev Frontend | Implement | Review |  |  |  |  | Detail armada + lokasi pickup/dropoff
1.4 Checkout (add_to_cart + begin_checkout) | Phase 1 | Dev Frontend |  | Implement | Review |  |  |  | add_to_cart + begin_checkout + parameter lokasi
1.5 Promo (select_promotion — opsional) | Phase 1 | Dev Frontend |  | Implement | Review |  |  |  | Hanya jika promo digunakan. coupon + promo_status
1.6 Payment Detail (add_payment_info + proceed_to_payment) | Phase 1 | Dev Frontend |  |  | Implement | Review |  |  | Total + platform_fee. Key event sementara: proceed_to_payment
2.1 Redirect ke Nicepay (redirect_to_payment_gateway) | Phase 2 | Dev Frontend |  |  | Implement | Review |  |  | Handoff cross-domain. parameter: payment_gateway, order_id, value
2.2 Return dari Nicepay (return_from_payment_gateway) | Phase 2 | Dev Frontend |  |  |  | Implement | Review |  | Baca status backend. Jangan kirim purchase hanya karena load success
3.1 Purchase / Booking Success (purchase + booking_success) | Phase 3 | Dev Backend |  |  |  | Implement | Review |  | Validasi transaksi dari backend. transaction_id unik + dedup
3.2 Failed / Cancelled / Expired Events | Phase 3 | Dev Backend |  |  |  |  | Implement | Review | Event untuk payment_status selain success
4.1 GTM Preview & GA4 DebugView QA | Phase 4 | Ade / QA | [5 empty] | QA | QA setiap event di GTM Preview + GA4 DebugView
4.2 Set Key Events & Conversion di GA4 | Phase 4 | Ade | [5 empty] | Set | proceed_to_payment (sementara) → purchase (final)
4.3 Looker Studio Report Setup | Phase 4 | Ade | [5 empty] | Build | Dashboard funnel + conversion report
Legend:
Blue
Yellow
Green

## Data Layer Tracker
Implementation Data Layer Tracker — Tim Developer
No | Event Name | Type | Trigger / Step | Required Parameters | Optional Parameters | Phase | Status | Notes / Kendala
1 | virtualPageview | Custom | Setiap route SPA dimuat | page_path, page_title | previous_path | Phase 1 | Not Started | Tandai tiap perpindahan step SPA
2 | search | Standard GA4 | Klik tombol 'Cari Armada' | service, pickup_area, pickup_date, pickup_time, duration_hours | rental_end | Phase 1 | Not Started | Search intent parameter
3 | view_item_list | Standard GA4 | Halaman daftar armada dimuat | item_list_name, items[].item_id, item_name, item_category, price | item_variant | Phase 1 | Not Started | Reset ecommerce: null sebelum push
4 | select_item | Standard GA4 | Klik tombol 'Pilih' armada | item_list_name, items[1].item_id, item_name, price |  | Phase 1 | Not Started | Hanya 1 item terpilih
5 | view_item | Standard GA4 | Halaman detail 'Sewa di [lokasi]' dimuat | currency, value, items[1].item_id, item_name, price |  | Phase 1 | Not Started | value = tarif belum termasuk platform fee
6 | fill_rental_detail | Custom | Lokasi jemput/antar terisi (on-blur) | pickup_location, dropoff_location | same_as_pickup, driver_note | Phase 1 | Not Started | Pisahkan dari pickup_area di form search
7 | add_to_cart | Standard GA4 | Klik 'Lanjutkan ke Detail Pemesanan' | currency, value, items[1], pickup_location, dropoff_location | same_as_pickup, driver_note | Phase 1 | Not Started | Parameter lokasi wajib mulai di sini
8 | begin_checkout | Standard GA4 | Halaman 'Informasi Pemesanan' dimuat | currency, value, items[1] |  | Phase 1 | Not Started | Sama seperti add_to_cart, ganti event
9 | select_promotion | Custom | Klik 'Gunakan Promo' | coupon, promo_status |  | Phase 1 | Not Started | Opsional — hanya jika promo dipakai
10 | add_payment_info | Standard GA4 | Ringkasan 'Detail Pembayaran' dimuat | currency, value (tarif + platform_fee), tariff, platform_fee, items[1] | coupon | Phase 1 | Not Started | value = total dibayar
11 | proceed_to_payment | Custom | Klik 'Lanjutkan ke Pembayaran' + lolos reCAPTCHA | currency, value, tariff, platform_fee, items[1] |  | Phase 1 | Not Started | KEY EVENT SEMENTARA — sebelum purchase aktif
12 | redirect_to_payment_gateway | Custom | Tepat sebelum redirect ke Nicepay | payment_gateway, order_id, value |  | Phase 2 | Not Started | Cross-domain handoff — di luar GTM Bluebird
13 | return_from_payment_gateway | Custom | Kembali dari Nicepay ke Bluebird LP | payment_status, transaction_id, order_id | booking_id | Phase 2 | Not Started | Baca status backend — jangan kirim purchase otomatis
14 | purchase | Standard GA4 | Halaman success + status = success | transaction_id, value, currency, items[1], payment_status | tariff, platform_fee, coupon | Phase 3 | Not Started | KEY EVENT FINAL — transaction_id unik dari backend
15 | booking_success | Custom | Alternatif purchase (jika purchase bermasalah) | transaction_id, booking_id, value, payment_status |  | Phase 3 | Not Started | Fallback jika GA4 standard purchase tidak cocok

## GTM Implementation
Google Tag Manager Implementation Tracker
No | Tag Name | Trigger Type | Trigger Detail | Data Layer Variable(s) | GA4 Event / Type | Status | Notes
1 | GA4 - Virtual Pageview | Custom Event | event = virtualPageview | page_path, page_title, previous_path | GA4 Config / page_view (set via GTM) | Not Started | GTM Variable: DLV page_path, DLV page_title
2 | GA4 - Search | Custom Event | event = search | service, pickup_area, pickup_date, pickup_time, duration_hours, rental_end | GA4 Event / search | Not Started | Set search_term parameter dari pickup_area
3 | GA4 - View Item List | Custom Event | event = view_item_list | ecommerce.item_list_name, ecommerce.items[] | GA4 Event / view_item_list | Not Started | Reset ecommerce: null sebelum fire
4 | GA4 - Select Item | Custom Event | event = select_item | ecommerce.item_list_name, ecommerce.items[] | GA4 Event / select_item | Not Started | Hanya 1 item di items[]
5 | GA4 - View Item | Custom Event | event = view_item | ecommerce.currency, ecommerce.value, ecommerce.items[] | GA4 Event / view_item | Not Started | Value = tarif (belum + platform_fee)
6 | GA4 - Fill Rental Detail | Custom Event | event = fill_rental_detail | pickup_location, dropoff_location, same_as_pickup, driver_note | Custom Event / fill_rental_detail | Not Started | GTM Variable: DLV masing-masing
7 | GA4 - Add to Cart | Custom Event | event = add_to_cart | ecommerce.*, pickup_location, dropoff_location | GA4 Event / add_to_cart | Not Started | Reset ecommerce + push parameter lokasi
8 | GA4 - Begin Checkout | Custom Event | event = begin_checkout | ecommerce.currency, ecommerce.value, ecommerce.items[] | GA4 Event / begin_checkout | Not Started | Sama dgn add_to_cart tanpa parameter lokasi
9 | GA4 - Select Promotion | Custom Event | event = select_promotion | coupon, promo_status | Custom Event / select_promotion | Not Started | Opsional
10 | GA4 - Add Payment Info | Custom Event | event = add_payment_info | ecommerce.value, tariff, platform_fee, coupon, ecommerce.items[] | GA4 Event / add_payment_info | Not Started | Value = tariff + platform_fee
11 | GA4 - Proceed to Payment | Custom Event | event = proceed_to_payment | ecommerce.value, tariff, platform_fee, ecommerce.items[] | Custom Event / proceed_to_payment | Not Started | KEY EVENT SEMENTARA
12 | GA4 - Redirect to Gateway | Custom Event | event = redirect_to_payment_gateway | payment_gateway, order_id, value | Custom Event / redirect_to_payment_gateway | Not Started | Terakhir sebelum cross-domain
13 | GA4 - Return from Gateway | Custom Event | event = return_from_payment_gateway | payment_status, transaction_id, order_id | Custom Event / return_from_payment_gateway | Not Started | Jangan kirim purchase otomatis
14 | GA4 - Purchase | Custom Event | event = purchase | transaction_id, ecommerce.value, currency, ecommerce.items[], payment_status | GA4 Event / purchase | Not Started | KEY EVENT FINAL — dedup via transaction_id
15 | GA4 - Booking Success (fallback) | Custom Event | event = booking_success | transaction_id, booking_id, value, payment_status | Custom Event / booking_success | Not Started | Fallback jika purchase bermasalah

## Requirements
Bluebird Journey Tracking — List Requirements
No | Category | Requirement | Source (Section) | Priority | Status | Notes
1 | Teknis | SPA route change harus trigger virtualPageview | Sec 1, Sec 5.1 | High | Not Started | page_path & page_title per step
2 | Teknis | Reset ecommerce: null sebelum setiap push event baru | Sec 8.1 | High | Not Started | Mencegah data bertumpuk antar-step
3 | Teknis | transaction_id harus dari backend & unik (bukan frontend) | Sec 8.2 | High | Not Started | Anti duplicate purchase saat refresh
4 | Teknis | item_id pakai ID fleet stabil dari backend, bukan nama display | Sec 4.3, Sec 8.5 | High | Not Started | Butuh konfirmasi ketersediaan dari developer
5 | Teknis | value/price selalu numeric (bukan string) | Sec 8.5 | Medium | Not Started | GA4 requirement
6 | Teknis | Pisahkan pickup_area (form search) dan pickup_location (detail) | Sec 4.2 | High | Not Started | Supaya analisis area populer vs titik jemput aktual tidak kacau
7 | Teknis | value = total yang dibayar (tariff + platform_fee), kirim tariff & platform_fee sebagai parameter terpisah | Sec 8.4 | High | Not Started | Konsisten di semua event
8 | Teknis | Parameter kosong dikirim sebagai null atau tidak disertakan: jangan undefined | Sec 8.5 | Medium | Not Started | JS strict mode
9 | Teknis | Konfirmasi session GA setelah login di tengah funnel | Sec 8.3 | Medium | Not Started | Jika session berganti, funnel terputus
10 | Teknis | Armada non-aktif: perlu putuskan apakah tetap dikirim dengan penanda | Sec 5.2 | Low | Not Started | Goldenbird Luxury EV hanya untuk sewa >2 jam
11 | Teknis | Implementasi Nicepay cross-domain — tracking di luar GTM Bluebird | Sec 5.6, Sec 6 | High | Not Started | Tidak dapat dilacak oleh GTM Bluebird
12 | Teknis | Satu user action = satu event (fire sekali; hindari duplikat) | Sec 8.5 | Medium | Not Started | Back/forward/refresh handling
13 | Event | Implementasi 5.1 Entry & Search (virtualPageview + search) | Sec 5.1 | High | Not Started | Form pencarian 'Sewa Mobil'
14 | Event | Implementasi 5.2 Daftar Armada (view_item_list + select_item) | Sec 5.2 | High | Not Started | Halaman 'Layanan tersedia'
15 | Event | Implementasi 5.3 Detail Sewa & Lokasi (view_item + fill_rental_detail) | Sec 5.3 | High | Not Started | Halaman 'Sewa di [lokasi]'
16 | Event | Implementasi 5.4 Masuk Checkout (add_to_cart + begin_checkout) | Sec 5.4 | High | Not Started | Mulai parameter lokasi wajib
17 | Event | Implementasi 5.5 Pembayaran & Payment Intent (add_payment_info + proceed_to_payment) | Sec 5.5 | High | Not Started | Tetapkan proceed_to_payment sebagai key event sementara
18 | Event | Implementasi 5.6 Redirect Nicepay (redirect_to_payment_gateway) | Sec 5.6 | High | Not Started | Handoff cross-domain
19 | Event | Implementasi 5.7 Return & Success (return_from_payment_gateway + purchase) | Sec 5.7 | High | Not Started | Baca status backend sebelum kirim event
20 | Event | Implementasi rental_duration_warning (opsional — modal min 4 jam) | Sec 5.3 (Image 4) | Low | Not Started | Mengukur friksi durasi sewa
21 | QA | QA via GTM Preview Mode sebelum publish | Sec 8.5, Sec 9 | High | Not Started | Setiap event harus terverifikasi
22 | QA | QA via GA4 DebugView — validasi parameter setiap event | Sec 8.5, Sec 9 | High | Not Started | Cek parameter wajib vs opsional
23 | QA | Set Key Events / Conversions di GA4 | Sec 9 | Medium | Not Started | proceed_to_payment (sementara) → purchase (final)
24 | QA | Siapkan Looker Studio report untuk funnel & conversion | Sec 9 | Medium | Not Started | Dashboard untuk monitoring performa
25 | Data | Parameter Dictionary lengkap (20+ parameter) — acuan developer & GTM | Sec 7 | High | Not Started | Sudah terdokumentasi di brief Section 7